RE-ADVERTISMENT - TERMS OF REFERENCE (TOR) EVALUATION OF THE AKELIUS LANGUAGE PROJECTS IMPLEMENTED BY SOS CHILDREN’S VILLAGES

Table of Contents

1.	Introduction	1

2.	Background	2

3.	Objectives of the Evaluation	3

4.	Scope of the Evaluation	5

5.	Expertise Required for the Evaluator (Somalia national or resident)	5

6.	Evaluation Approach and Methodology	5

7.	Supervision and Management	7

8.	Terms and Conditions	7

9.	Application Requirements	7

10.	Evaluation Criteria for Selection	7

11.	Timeline	8

## Introduction

About SOS Children’s Villages

SOS Children’s Villages is the world’s largest non-governmental organization dedicated to supporting children and young people without parental care or at risk of losing it. Founded in 1949 in Austria, the organization operates in over 130 countries and territories, providing tailored care solutions that prioritize the best interests of each child.

The organization's mission is to ensure that every child grows up with the care, relationships, and support they need to become their strongest selves. This is achieved through a combination of family-like care, family strengthening programs, education, health care, and emergency relief efforts.

SOS Children’s Villages works in partnership with communities, governments, and other organizations to advocate for children's rights and to influence policies that affect their well-being. The organization's approach is grounded in the UN Convention on the Rights of the Child, while its Humanitarian Mandate steers the organization’s work in emergency settings, where it seeks to prevent family separation, protect children and youth, and ensure care for unaccompanied or separated children. In 2025, the organization carried out 119 humanitarian projects in 41 countries, reaching more than 2,7 million individuals, most of them children.

SOS Children’s Villages Sweden, the Swedish member association, supports international programmes through fundraising, advocacy, and technical assistance. It is one of the main funders of humanitarian programs in the Federation and it currently funds emergency interventions in the Middle East, East Africa and Latin-America, with a significant part of the funding used in education in emergency projects.

## Background

SOS Children’s Villages Sweden has carried out a long partnership with Akelius Foundation for program support internationally. Since 2024, SOS Children’s Villages Sweden (SOS Barnbyar) has supported SOS partner associations in implementing the Akelius digital learning platform, developed by Akelius Foundation, to enhance the language acquisition and digital skills development of children and youth, particularly in fragile, low-resource, and crisis-affected settings. These partnerships strengthen SOS Children’s Villages Sweden’s positioning in humanitarian programming, particularly within Education in Emergencies (EiE).

SOS Barnbyar currently partners with a total of 10 national associations for implementation of Akelius Language projects. These national associations are those of Colombia, Ghana, Ethiopia, Bangladesh, Mozambique, Uganda, Somalia, Sudan, South Sudan and Lebanon. In eight of these associations, the programmatic framework is Education in Emergencies, as the projects seek to address critical gaps in language and digital literacy as a result of crises, mostly related to conflict and forced migration. The duration of the projects varies between 1 and 5 years, with an average length of two years. Funding is provided mainly for the purchase of ICT equipment, refurbishment of ICT rooms, classrooms or child-friendly spaces, solar panels and supporting equipment, training and incentives for teachers, sensitization or enrolling sessions in communities, and SOS project staff. Although Akelius Learning also includes a math component, projects in humanitarian settings have so far implemented uniquely the language learning programme.

The Akelius Language projects seek to improve inclusive and equitable language learning outcomes for children and youth (6 to 18 years) in vulnerable and crisis-affected contexts through the effective integration of digital learning technologies using a self-paced learning approach. The project’s main outcomes can be summarized as:

- Improved access to quality digital learning environments: Children and youth have increased access to safe, inclusive, and well-equipped ICT-enabled learning spaces that support self-based language acquisition.

- Strengthened capacity of teachers and education systems: Teachers, facilitators, and education stakeholders enhance their digital, pedagogical, and blended learning competencies to effectively deliver language education.

- Enhanced language proficiency and engagement among learners: Children and youth demonstrate improved language skills, digital literacy, and sustained engagement in learning supported by family, community and institutional uptake of digital education approaches.

The projects use different Result Frameworks as well as a consolidated monitoring tool which gathers the following anonymized data on a monthly basis:

- Students: new students, active students, students who discontinued, and number of students who pass to the next level (between A1 and B2). Students are disaggregated per gender (female/male), age (<12 years/ > 12 years) and students with a disability.

- Teachers: teachers trained in Akelius Language Course (ALC), new teachers teaching ALC, number of teachers using ALC, average teaching hours/week, lesson’s duration

- Hardware purchased

- Type of analogue material received

- Classrooms built or renovated

- PV panels

In 2025, 6 893 students were enrolled in SOS-supported Akelius Language projects in six countries (four countries had not begun implementing).

## Objectives of the Evaluation

The objective of this evaluation is to assess the relevance, coherence, effectiveness, efficiency, impact and sustainability of the Akelius Programme in crises settings, in line with the OECD-DAC evaluation criteria. The evaluation will generate evidence for accountability and learning, supporting the strategic progression of SOS Children’s Villages Sweden as an enabler of education in emergency projects within the SOS Children's Villages Federation.

The evaluation aims to inform:

- Akelius Foundation’s understanding of the projects’ impact on equitable, inclusive and safe access to education and digital literacy for children and youth in crises settings.

- SOS Children’s Villages Sweden’s alignment with, and further support of, education in emergency initiatives across the Federation.

- SOS national association’s assessment of their capacity, limitations and impact in ensuring measurable outcomes in challenging operational contexts.

The evaluation will assess three programmatic objectives:

Part 1. Impact of the project on digital language learning:

- Evaluate if the project enhances children and youth’s language learning

- Deep dive into the effectiveness of the digital platform for language acquisition gains in different groups of children, considering: 1. Children as disaggregated in the monitoring tool (gender/age), 2. Refugee or displaced children, 3. Children with at least one reported disability, 4. Children from the host community

- Identify patterns of exclusion, lower engagement, or systematically lower gains for specific sub-groups, and their underlying causes

Part 2. Contribution to local system strengthening:

- Contribution to teacher/facilitator digital and pedagogical capacity development

- Strengthening of a safe educational environment (incl. training and awareness on child and youth safeguarding)

- Engagement of community structures supporting education access

Part 3. Framing of the project in the crisis-response strategy:

- Assess the relevance of the Akelius approach to address educational needs, including those of children living with disabilities

- Evaluate the criteria used in how learners and the geographical area were selected, in line with international humanitarian standards adopted by the SOS Children’s Villages Federation

- Assess how program participants, caregivers and other key stakeholders were identified and engaged in the evaluated projects, including in their design and implementation

- Reflect upon the project’s added value in the overall emergency response framework (both the local emergency response and the SOS partner organization)

- Explore the integration and adoption of data protection, safeguarding measures and Accountability to Affected Populations

Specific Objectives of the Evaluation

The evaluation will respond to the following specific objectives, aligned with the OECD-DAC criteria. For each criterion, evaluators are encouraged to explore both qualitative and quantitative evidence and consider leading questions that help frame their analysis.

- Relevance -is the intervention doing things right?

Leading questions:

Does the project enhance language learning in children living in crises settings?

Are there main disparities in language acquisition within different groups of learners?

How is the project and learning method addressing the needs of children living with disabilities?

- Coherence -how well does the intervention fit?

Leading questions:

To what extent does the Akelius Language project fit within the National Association’s emergency or humanitarian response strategy?

Is the project aligned with globally recognized humanitarian standards and EiE standards?

Does the project enhance the partner organization’s role as humanitarian actor?

Is the project complementary to other interventions within child protection, mental health, healthcare, nutrition, or education in emergencies?

- Effectiveness -is the intervention achieving its objectives?

Leading question:

To what extent does the Akelius Language Project achieve its intended outcomes when it comes to:

- Improving language proficiency

- Strengthening teacher capacity such as their pedagogical and digital skills

- Increasing engagement from key stakeholders such as governmental institutions, parents and community leaders?

- Efficiency -how well are resources (financial, human and material) being used?

Leading question:

How has the project used available resources to achieve main outcomes and how have outcomes being impacted from working in low-resource settings, migrant routes or conflict areas?

- Impact -what difference does the intervention make?

Leading questions:

Does the project enhance learner’s language and digital skills?

Does the project contribute to improvements in academic performance?

Have key stakeholders such as parents, school staff and the community changed their attitudes regarding support to children on language acquisition through digital learning?

Has the project had any effects on teachers’ perspectives regarding children’s rights to education and child and youth safeguarding?

- Sustainability -will the benefits last?

Leading questions:

Does the project address issues of sustainability regarding digital infrastructure in low-income settings?

Does the partner association have risk management capacities in relation to the project and have there been risk assessments done?

Does the partner association have an exit strategy?

Has the partner association assured responsible management of the technical equipment after the project ends?

## Scope of the Evaluation

- Geographic scope: Somalia (Mogadishu and Baidoa), Ethiopia (Midega Tola)

- Timeframe covered: September - December 2026

- Thematic areas: Education in emergencies, core humanitarian standards, child protection in humanitarian action

- Stakeholders: Children and youth, teaching staff and school staff, families, CBOs, community leaders, local authorities, SOS partner organizations.

## Expertise Required for the Evaluator (Somalia national or resident)

- Project management experience, preferably in the humanitarian or development sector

- Proven experience conducting multi-country evaluations, particularly in Sub-Saharan Africa

- Strong expertise in rights-based and humanitarian programming evaluations

- Advanced academic background in social sciences, child rights, international development, or related fields

- Experience applying qualitative and quantitative methodologies

- Demonstrated experience conducting participatory and ethical research involving children and vulnerable populations

- Strong understanding of child rights and humanitarian contexts

- Fluency in English; knowledge of local languages in Somalia or Ethiopia is considered an asset

- Excellent analytical, writing, and facilitation skills

## Evaluation Approach and Methodology

The evaluation will be structured in three distinct phases, each with specific deliverables:

Inception Phase

- Review of programme documentation (including SOS monitoring tools), humanitarian and Education in Emergency standards, Core Humanitarian Standards, Unicef-Akelius Digital Learning evaluations and reports, SOS Humanitarian Mandate, SOS’ Companion Handbook, SOS partner organizations’ humanitarian strategy, humanitarian context where the projects take place.

- Development of an inception report including evaluation matrix, refined methodology, sampling approach, and draft data collection tools.

- Presentation of methodology and workplan to the coordination group for validation.

Fieldwork Phase

- Field visits to selected sites in Somalia and Ethiopia

- Key informant interviews (KIIs), focus group discussions (FGDs), and participatory methods involving children, caregivers, teachers, CBOs, and local and school authorities.

- Debrief sessions with SOS partners and stakeholders to share preliminary findings.

Synthesis and Feedback Phase

- Data triangulation and final analysis, including:

  - Evidence based and actionable recommendations

  - Formulation of minimum implementation standard for digital language learning impact across contexts

  - Monitoring requirements for the SOS supported Akelius projects

- Submission of draft report and integration of feedback.

- Finalization of deliverables and dissemination of findings.

Throughout all phases, evaluators are expected to apply ethical standards in line with SOS Children’s Villages' Child and Youth Safeguarding Policy and international guidelines for research involving children.

The evaluator(s) should propose a mixed-methods approach tailored to the programme’s complexity and the multi-country context. The methodology must:

- Be participatory and based on rights.

- Include theory-based evaluation such as theory of change.

- Rely on both primary data collection (interviews, FGDs, surveys) and document review.

- Apply the highest standard of child protection and research ethics, especially in work with children and youth.

Triangulation across data sources is expected to ensure validity. The Evaluator must ensure methodological consistency across countries and propose minimum data collection and data management standards for multi-country evaluations.

## Supervision and Management

The evaluation will be commissioned by SOS Barnbyar Sverige and managed in coordination with SOS partner organizations and SOS Humanitarian Action Team. A core evaluation coordination group will be established, including representatives from all these three constellations. This group will:

- Provide guidance and feedback during inception, data collection, and reporting.

- Facilitate access to key documents and stakeholders.

- Ensure alignment with SOS Children Villages Sweden’s expectations and support ethical compliance.

## Terms and Conditions

- The consultant is responsible for their own income tax, insurance, and compliance with local labour laws.

- All evaluators must commit to and sign SOS Children’s Villages’ Child and Youth Safeguarding Policy and Code of Conduct.

- Travel and accommodation costs, if applicable, should be included in the financial proposal.

- SOS Children’s Villages Sweden will coordinate access to stakeholders and documentation.

- A contract outlining scope, deliverables, and payment schedule will be signed upon selection.

## Application Requirements

Interested consultants or firms are invited to submit:

- A technical proposal outlining the methodology, work plan, and understanding of the assignment (max 5 pages).

- CVs of all proposed team members.

- Financial proposal in EUR, inclusive of all costs.

- Two references from recent relevant evaluations or reports.

- A sample of a similar evaluation report (if available).

Proposals must be submitted electronically to procurement@sossomalia.org by 4:00PM on 15th July 2026. Late submissions will be rejected.  Please use the subject line: “Evaluation Proposal – Akelius Language”.

## Evaluation Criteria for Selection

Proposals will be reviewed based on the following criteria:

- Methodology and Approach: Suitability, clarity, and rigor of the proposed methods.

- Experience and Expertise: Relevance of past evaluations and team qualifications.

- Feasibility and Work Plan: Realistic and coherent timeline and resource use.

- Cost-effectiveness: Value for money within the budget ceiling.

## Timeline

The consultancy is expected to take place between September and December 2026

| Phase | Deliverable | Timeframe |
| --- | --- | --- |
| Inception | Inception Report (methodology, tools, work plan) | Early September 2026 |
| Preparation | Minimum data standards, translated tools, logistics | Late September 2026 |
| Fieldwork | Data collection | October-November 2026 |
| Initial Analysis | Early findings and debrief with stakeholders | Late November 2026 |
| Drafting | Draft Evaluation Report | Early December 2026 |
| Finalization | Final Report and Summary Brief, Presentation of findings | Mid-December 2026 |

Data Protection and Privacy

By submitting an application in response to this Terms of Reference, applicants consent to SOS Children’s Villages collecting, processing, storing, and using their personal data for the purposes of managing the recruitment and selection process, assessing qualifications, conducting due diligence where applicable, and maintaining records related to the procurement process. Personal data will be handled in accordance with applicable data protection legislation and SOS Children’s Villages’ privacy and data protection policies. Applicants may request access to, correction of, or deletion of their personal data, subject to applicable legal and contractual obligations.