## BoQs Taleh,Fiqi Fuliyeh
ANNEX NO: 1 - NIS BOQ
Project: 2522307
Donor: RNE/SDC
Date: 23/07/2026
BoQ for PROSPERIS distribution and installation of Solar Streetlights in North East locations - 75 SSL
1. BoQ for the Concrete Foundation and Installation of 40 Solar Street Lights in Taleh
Item | Description | Unit | Qty | Unit Price (USD) | Total Price (USD)
1 | Mobilisation, preliminary works, clearing of site , site establishment including all required necessary construction materials and tools. | Pole | 40
2 | Earthwork in excavation of trench for foundation of the pole, in all kinds of soil and not exceeding 1.2m depth and the Area is (0.7*0.7)m², including dressing of bottom and sides of trenches. Stack excavated soil clear from edges of excavation, disposal of surplus soil out of site as directed by engineer. | m³ | 23.52
3 | Plain Cement concrete providing stirrups holding the four bars used to hold the solar plate through bolts for column foundation of the pole,debth is 1.2m of the hole plus 0.8m above the ground level, at the top the area is (50*50)m² and total area up to the surface is (0.7*0.7)m²with cement concrete 1:2:4 (1 cement : 2 clean coarse sand : 4 stone aggregate of 25mm down) | m³ | 39.2
4 | Welding of anchor bolts with 4 stirrups | Pcs | 40
5 | Electrical and Mechanical works for the installation of the complete pole onto the concrete foundation with proper wiring. This includes crane renting for mounting the pole | Days | 16
6 | Security fees during the installation period | Days | 16
| Total for the Concrete Foundation & installation of 40 Solar Street Lights in Taleh |  |  |  | 0
2. BoQ for the Concrete Foundation and Installation of 20 Solar Street Lights in Fiqi fuliyeh
Item | Description | Unit | Qty | Unit Price (USD) | Total Price (USD)
1 | Mobilisation, preliminary works, clearing of site , site establishment including all required necessary construction materials and tools. | Pole | 20
2 | Earthwork in excavation of trench for foundation of the pole, in all kinds of soil and not exceeding 1.2m depth and the Area is (0.7*0.7)m², including dressing of bottom and sides of trenches. Stack excavated soil clear from edges of excavation, disposal of surplus soil out of site as directed by engineer. | m³ | 11.76
3 | Plain Cement concrete providing stirrups holding the four bars used to hold the solar plate through bolts for column foundation of the pole,debth is 1.2m of the hole plus 0.8m above the ground level, at the top the area is (50*50)m² and total area up to the surface is (0.7*0.7)m²with cement concrete 1:2:4 (1 cement : 2 clean coarse sand : 4 stone aggregate of 25mm down) | m³ | 19.6
4 | Welding of anchor bolts with 4 stirrups | Pcs | 20
5 | Electrical and Mechanical works for the installation of the complete pole onto the concrete foundation with proper wiring. This includes crane renting for mounting the pole | Days | 12
6 | Security fees during the installation period | Days | 12
| Total for the Concrete Foundation & installation of 20 Solar Street Lights in Fiqi fuliyeh |  |  |  | 0
3. BoQ for the Concrete Foundation and Installation of 15 Solar Street Lights in Biyogadud
Item | Description | Unit | Qty | Unit Price (USD) | Total Price (USD)
1 | Mobilisation, preliminary works, clearing of site , site establishment including all required necessary construction materials and tools. | Pole | 15
2 | Earthwork in excavation of trench for foundation of the pole, in all kinds of soil and not exceeding 1.2m depth and the Area is (0.7*0.7)m², including dressing of bottom and sides of trenches. Stack excavated soil clear from edges of excavation, disposal of surplus soil out of site as directed by engineer. | m³ | 8.82
3 | Plain Cement concrete providing stirrups holding the four bars used to hold the solar plate through bolts for column foundation of the pole,debth is 1.2m of the hole plus 0.8m above the ground level, at the top the area is (50*50)m² and total area up to the surface is (0.7*0.7)m²with cement concrete 1:2:4 (1 cement : 2 clean coarse sand : 4 stone aggregate of 25mm down) | m³ | 14.7
4 | Welding of anchor bolts with 4 stirrups | Pcs | 15
5 | Electrical and Mechanical works for the installation of the complete pole onto the concrete foundation with proper wiring. This includes crane renting for mounting the pole | Days | 8
6 | Security fees during the installation period | Days | 8
| Total for the Concrete Foundation & installation of 15 Solar Street Lights in Biyogadud |  |  |  | 0
| Grand Total for the Concrete Foundation & installation of 75 Solar Street Lights - All 3 locations |  |  |  | 0